## REGRESSION(Main Sheet)
REGRESSION TESTING DOCUMENTATION OF 369DESKTOP APPLICATION
Objectives: | verifying that the product works as expected after a change has been made, ensuring that the basic functionality of the product is working, and so on.
S NO. | Module | Test Scenario | Testing environment | Status | Remarks
1 | Launch | Time taken to launch | 1.Google chrome | 1.20sec
2.Firefox
3.Windows
4.Mac
2 | Login Page | Login Features | 1:Responsive Text Field | working
|  |  | 2.Credential Entry in Text Field | working
|  |  | 3.Forget me button | working
|  |  | 4.Checkbox | working
|  |  | 5.Sign in Button | working
|  |  | Login time taken | 24.05sec.
3 | Home Page | Check all Menu List | 1.Registration | working | Recents module fixed
|  |  | 2.Phone module | working
|  |  | 3.IM module | working
|  |  | 4.Recent module | not working
|  |  | 5.Contacts module | working
|  |  | 6.Settings module | working
|  |  | 7.Voicemails module | working
|  |  | 9.Logout module | working
|  |  | 10.Refresh | working
|  |  | 11.Logout | working
|  |  | 12.logout time taken | 1min.18 sec.
|  |  | 13. Refresh time taken | 33.16sec
14. whenever we move our cursor into the refresh icon it should show the name of the refresh button and the logout button.
-
4 | Phone Tab | Functionality | 1.Text Field | working
|  |  | 2.Backspace button | working
|  |  | 3.Dialpad | working
|  |  | 4.Voice Calling button | working
|  |  | 5.Video calling button | working
|  |  | 6.Conference call feature | working
Check both Windows and Mac app
|  | Voice Call | 1.DT app to Web app | working
2.DT app to Android app
|  |  | 3.DT app to Windows app | working
Video Call
|  |  | 1.DT app to Web app | working
2.DT app to Android app
3.DT app to Windows app
|  | Calling | 1. Is there a Time Limit | yes
|  |  | 2.Voice quality | Good
|  |  | 3.Video Quality | Good
4.Call Waiting
6 | Recent Tab | Functionality
NOT OPEN
-
-
-
7 | Contacts Tab | Functionality | 1. Contact List | working
8 | Settings Tab | Speed Dial | 1.Working or not
2.Is there any limit of no. of contacts in speed dial
|  | Functionality | 1.Checkboxes | working
|  |  | 2.Text Field | working
9 | Voicemails Tab | Functionality | 1.Checkboxes | working
|  |  | 2.Scroll bar | working

## Regression Test
REGRESSION TESTING DOCUMENTATION OF 369 WINDOWS DESKTOP APPLICATION
Objectives: | verifying that the product works as expected after a change has been made, ensuring that the basic functionality of the product is working, and so on.
S NO. | Module | Test Scenario | Testing environment | Status
1 | Launch | Time taken to launch | 1.Google chrome
2.firefox
3.windows
4. Mac
2 | Login Page | Login Features | 1:Responsive Text Field
2.Credential Entry in Text Field
3.Forget me button
4.Remember me
5.Sign in Button
3 | Home Page | Check all Menu List | 1.Signal
2.Phone module
3. IM module
4. Recent module
5.Contacts module
6.Settings module
7.Voicemails module
8.Refresh Button
9.Logout Button
4 | Phone Tab | Features | 1.Text Field
2.Backspace button
3. Dialpad
4. Voice Calling button
5.video calling button
6.Conference call feature
Outgoing voice calls
|  | Voice calling | 1.Windows DT app to Web app
2.Windows DT app to android app
3.Windows DT app to MAC DT app
4.Windows DT app to Landline number
5.Windows DT app to IOS app
6.Windows DT app to GS wave lite app
7.Windows DT app to Grandstream
8.Windows DT app to Windows DT app
Incoming voice calls
10. Web app to DT app
11. Android to DT app
12. Windows app to DT app
13. Landline number to DT app
14. IOS app to DT app
15. Android app to DT app
16. Grandstream to DT app
17. GS wave Lite app to DT app
18. Extension to DT app
|  | Video calling | Outgoing video calls
1.Windows DT app to Web app
2.Windows DT app to android app
3.Windows DT app to MAC DT app
4.Windows DT app to Landline number
5.Windows DT app to IOS app
6.Windows DT app to GS wave lite app
7.Windows DT app to Grandstream
8.Windows DT app to Windows DT app
Incoming Video calls
10. Web app to DT app
11. Android to DT app
12. Windows app to DT app
13. Landline number to DT app
14. IOS app to DT app
15. Android app to DT app
16. Grandstream to DT app
17. GS wave Lite app to DT app
18. Extension to DT app
|  | Calling third window | 1. Transfer Button is cilickable or not
5 |  |  | 2.Add Call Button is cilickable or not
3.Swap Call Button is cilickable or not
4.Hold Button is cilickable or not
5.Mute Button is cilickable or not
6.Hangup Button is cilickable or not
7. Transfer Call feature is working or not
8. Add Call feature is working or not
9. Swap Call feature is working or not
10.Hold Button Working or not
11.Mute Button working or not
|  | Conference | 1. Voice Conference Call
2. Video Conference Call
3. Time Limit of calling or not
4.Limit of Adding no. of people on call or not
5.DT windows app
6.DT MacOS app
7.Mobile App IOS
8.Mobile app Android
9. GS wave lite app
10.SIP phone
| IM Tab | Functionality | 1. Did to Did ( sms)
2.Did to Phone number ( sms)
3.Extension to Mac DT app
4.Extension to Win DT app
5. Extension to mobile IOS app
6. Extension to GS wave lite app
7.Extention to Mobile ANdroid app
8.Extention to Offline Extention
9. Presence Feature
10.Only people with who we chat should be visible on the chat TAB
11.Latest received / sent chat on top
12.Latest chat detection
13.Chat reception & Transmission (Basic)
14. when you are in other tabs
15.Chat layout
16.Last message
17.Chat alignement (Transmission & Reception)
|  | Functionality and Page layout | 1. Text Field
2.Name display
3.Back Button
4.Scroll bar
6.Page Alignment
5.Received Message highlight
|  | Functionality | 1.Send SMS button
2.Chat List
3.Search Bar
4. Scroll bar
5. Voice Calling button
6 | Recent Tab | Functionality
7 | Contacts Tab | Functionality | 1. Contact List
2.Text Field
3.Search Button
4.Voice calling
5. Video Calling
6.Send SMS
7.Scroll Bar
8.External contacts button
8 | Settings Tab | Functionality | 1.Checkboxes
2.Text Field
|  | Speed Dial | 1. working or not
2. Is there any limit of no. of contacts in speed dial
9 | Voicemails Tab | Functionality | 1.Checkboxes
2.Scroll bar
3. Voicemails
10 | Extra | Timing | 1. Login Button
2.Voice quality
3.Video Quality
2.Registration
3.Refresh
4.Logout
|  | Call Recording | 1. outgoing call to mobile number.
2. outgoing to extension number.
3. incoming calls from extension to extension
4. incoming calls from mobile number to extension
5. incoming calls from mobile number to group.

## Sanity Testing
SANITY TESTING DOCUMENTATION OF 369DESKTOP APPLICATION
Objectives: | verifying that the product works as expected after a change has been made, ensuring that the basic functionality of the product is working, and so on.
S NO. | Module | Test Scenario | Testing environment | Status | Status | Status | Status | Status | status | status
|  |  |  | Date(17.02.2023) & Time(02:50) Tested By Arifa & Bhanu | Date(20.02.2023) & Time(16:6) Tested By Anjali, Saumya & yuvi | Date(21.2.2023) & Time(12:26) Tested By Anjali, Saumya & yuvi | Date(22.2.2023) & Time(12:26) Tested By Anjali, Saumya, Aurifa & yuvi | Date(24.2.2023) & Time(11:54) Tested By Anjali, Saumya, & yuvi | Date(28.2.2023) & Time(13:2) Tested By Anjali, Saumya, & sarika(hub369.links.com) | Date(1.3.2023) & Time(11:00) Tested By Anjali, Saumya, & sarika(hub369.links.com)
1 | Launch | Time taken to launch | 1.From windows | 16sec | 1 sec | 6 sec | 1 sec | 1 sec | 7 sec | 3 sec
2. from mac
2 | Login Page | Login Features | 1:Working or not | working | working | working | working | working | working | working
|  |  | 2.Time Taken | 25sec | 1 sec | 3 sec | 1 sec | 2 sec | 4 sec | 5 sec
3 | Home Page | Registration | 1.Signal | working | working | working | 1. Remember me is not there. 2. Registration is not there, it comes when we click on the phone tab.3.Third window is not there, it comes when clicking on the phone tab. | working(Remember me is not there.) | working | working
|  |  | 2.Time Taken | 7sec | 2 sec | 2 sec | 2 sec | 3 sec | 6 sec | 3 sec
|  |  | 3.Icons |  | .whenever we move our cursor into the refresh icon it should show the name of the refresh button and the logout button. | whenever we move our cursor into the refresh icon it should show the name of the refresh button and the logout button. | - | - | - | -
4 | Phone Tab | Functionality | 1.Voice call | working | working(but it is not connecting first time (after login and refresh) | working | working . | 1. working (but call is not connecting first time after login and refresh.) | 1. working (but the call is not connecting the first time after login and refresh.) | 1. working (but the call is not connecting the first time after login and refersh.)
|  |  | 2.Video call | working | working(same issue with video call) | working | working . | 1.working(but third window is not comming properly while video calling.) | 1. working (but the call is not connecting the first time after login and refresh.) | 1. working (but the call is not connecting the first time after login and refersh.)
|  |  | 3. Conference call | pending | 1. The call is not disconnecting(who lifted the call) after disconnecting the call (caller).2 dialer box is coming after lifting the call and once we click on ok in dialer box it is becoming one way speech. | pending |  | pending | working fine | working fine but sometimes it just re-directing to the voicemails even if the person is on the call.
|  |  | 4.Call Waiting | - | - | It is not working, which there is the tune of call waiting. | The popup is not coming. | pending | It is working But no popup coming. | 1. if caller 1 and caller 2 are on call and caller 1 put caller 2 on hold in order to add another call but in case caller 1 disconnects the call without caller3 being added to the call, caller 2 still remains on hold even if there is no one else on the call. 2. if caller 1 and caller 2 are on call and then caller 3 is being added by caller 1 meanwhile if caller 2 who is on hold disconnects so the call between caller 1 and caller 3 becomes one way call.
|  |  | 5.Add Call | [5 empty] | Working | 1. if caller 1 and caller 2 are on call and caller 1 put caller 2 on hold in order to add another call but in case caller 1 disconnects the call without caller3 being added to the call, caller 2 still remains on hold even if there is no one else on the call. 2. if caller 1 disconnects the call then both caller's 2 and 3 are on hold.
|  |  | 6.Transfer Call | [5 empty] | Working | Working
|  |  | 7. Swap Call | [5 empty] | Working | 1. two incoming calls can't be swapped
|  |  | 8. Marge Call | [5 empty] | When 2 caller or 3 caller disconnects the phone, then I get an extension from the person who disconnected the call while calling. | 1.call merge in working properly 2.If caller1 ends the call,caller 2 still stays on hold even if there is no one else is on call 3.if either of caller 2 or 3 ends the call then the call gets one way speech for caller 1
5 | IM Tab | Functionality | 1.Send Message | Able to send the message | Able to send the message. | Able to send the message. | Able to send the message | Able to send the message | Able to send the message | Able to send the message
|  |  | 2.Receive Message | did not receive the first message but nofication and popup is coming.second message received | not able to receive | not able to receive | not able to receive | not able to receive | not able to receive | Not able to receive
|  |  | 3.Notification | its working | Not working | Not working | Not working | Not working | Not working | Not working
7 | Contacts Tab | Functionality | 1. Contact List | its there | its there | its there | its there | its there | its there | is there
|  |  | 2.Search Box | working | working | working | working | working | working | working
|  |  | 3.voice call |  | Not able to call | working | The call is going after 2 sec and shows nop nop... and sometimes it shows undefined 2. form-filling coming on the screen. But sometime is working properly. | 1. working (but it is not connecting first time after login and refresh.) | working | working
|  |  | 4.vedio call |  | working | working | working | working | Video is coming but The voice is not coming | working
|  |  | 5.Messages |  | able to send a message but can't receive | able to send a message but can't receive | able to send a message but can't receive | able to send a message but can't receive | Not working | able to send message but can't recieve
8 | Settings Tab | Functionality | 1.Checkboxes |  | working | working | Not uploaded yet | Not Uploaded yet | working | working
|  |  | 2.Speed dial |  | its working | its working |  |  | not working | working
9 | Refresh | Functionality | 1. working or not | working | working | working | working but when the user clicks on refresh it's redirecting on the login page. | working but when the user clicks on refresh it's redirecting on the login page. | working fine | working
|  |  | 2. Time Taken | 30sec | 2 sec | 4 sec | 2 sec | 4 sec |  | 9 sec
10 | Logout | Functionality | 1.Working or not | working | working | working | working | working | working | working
|  |  | 2.Time taken | 13sec | 1 sec | 5 sec | 5 sec | 1 sec | 3 sec | 4 sec
11 | Voice Mail | Functionality | [5 empty] | Not uploaded yet | working | working
12 | Recent | Functionality | working or not | [5 empty] | Working | The recent window needs to be adjusted properly
|  |  | voice call | [5 empty] | Working | working
|  |  | 3.video call | [6 empty] | working

## Sanity Testing 03-03-2023
SANITY TESTING DOCUMENTATION OF 369DESKTOP APPLICATION
Objectives: | verifying that the product works as expected after a change has been made, ensuring that the basic functionality of the product is working, and so on.
S NO. | Module | Test Scenario |  | Testing environment | Status
Date(1.3.2023) & Time(2:00 pm) Tested By Anjali, Saumya, & sarika(tmp369.links.com)
1 | Launch | Time taken to launch |  | 1.From windows | 2 sec
2. from mac
2 | Login Page | Login Features |  | 1:Working or not | working but Rember me is not there.
2.Time Taken
3 | Home Page | Registration |  | 1.Signal | working
2.Time Taken
|  |  |  | 3.Icons | .whenever we move our cursor into the refresh icon it should show the name of the refresh button and the logout button.
4 | Phone Tab | Functionality |  | 1.Voice call | 1. working 2. The third window is not fit to the screen on the receiver side. 3. Hang-up button is not visible properly. 4. other button positions need to be adjusted properly on the screen of the third window.
|  |  |  | 2.Video call | 1. working 2. The third window is not fit to the screen on both sides (receiver and sender) 3. Hang-up button is not visible properly. 4. other button positions need to be adjusted properly on the screen of the third window.
|  |  |  | 3. Conference call | 1. working 2. The third window is not fit to the screen on both sides (receiver and sender) 3. Hang-up button is not visible properly. 4. other button positions need to be adjusted properly on the screen of the third window.
|  |  |  | 4.Call Waiting | for the second call it one-way speech
|  |  |  | 5.Add Call | 1. if caller 1 and caller 2 are on call and caller 1 put caller 2 on hold in order to add another call but in case caller 1 disconnects the call without caller3 being added to the call, caller 2 still remains on hold even if there is no one else on the call 2. if caller 1 disconnects the call then both caller's 2 and 3 are on hold.
|  |  |  | 6.Transfer Call | working but the third window is not coming properly and for caller 2 the first caller name is being displayed even after the call is transferred,
|  |  |  | 7. Swap Call | Working
|  |  |  | 8.Mute Button | when we put a call on mute it shows mute the call and the same goes for unmute and the mute button stays highlighted even if we unmute the call.
|  |  |  | 9. Merge Call | 1.call merge in working properly 2.If caller1 ends the call,caller 2 still stays on hold even if there is no one else is on call 3.if either of caller 2 or 3 ends the call then the call gets one way speech for caller 1
5 | IM Tab | Functionality |  | 1.Send Message | able to send message
|  |  |  | 2.Receive Message | can't receive them
|  |  |  | 3.Notification | no notification
6 | Contacts Tab | Functionality |  | 1. Contact List | is there
|  |  |  | 2.Search Box | it is working
|  |  |  | 3.voice call | yes it is working but it showing undefined when we call.
|  |  |  | 4.vedio call | working.
|  |  |  | 5.Messages | able to send messages but can't receive them,
7 | Settings Tab | Functionality |  | 1.Checkboxes | Not uploaded yet
2.Speed dial
8 | Refresh | Functionality |  | 1. working or not | working
|  |  |  | 2. Time Taken | 1 sec
9 | Logout | Functionality |  | 1.Working or not | working
|  |  |  | 2.Time taken | 3 sec
10 | Voice Mail | Functionality |  |  | The Window needs to adjust properly.
11
11 | Recent | Functionality |  | 1.working or not | working
User Experience
|  |  |  | 03-03-2023 by yuvi/anjali/saumya | Dev team status | testing team status | By yuvi(11-03)
1 | Sign In |  |  | Once we fill all credentials app should be able to sign once we press enter. | Fixed | yes its working | Yes working fine
2 | full |  |  | provide keyboard accessibility for app so that we will be able to navigate through interactive elements | Not a bug/ Will be taken up after bug fixing | -
3 | IM |  |  | there is no feature to search IM list by name or number | Assigned to Ankita/In Progress | progress | progress
4 | IM |  |  | Down arrow is not there to scroll down in IM list | Fixed | yes its working | Yes fixed
5 | recents |  |  | in call history, we need to show is it video call or audio call. | Can't be implemented as API does'nt provide this information | -
6 | Contacts |  |  | Names not getting filter by entering the name in search box | Assigned to Arpita/Completed | its working | Is it possible to make it work without hitting enter or seach button?
7 | Contacts |  |  | If I clear any name from the search bar, that data does not come as before. | Assigned to Arpita/Fixed/Merged/Deployed to tmp369links | its working | OKAY
8 | Voicemail |  |  | voicemail:- when we enter in voicemail section and when we play any voicemail for example:- I play first voicemail and then 2 and then 3 so that time all the voicemail play at a time means its plays simultaneously...it should be stopped and then play the next one. | Assigned to Sarika/Fixed/Merged/Deployed to tmp369links | its fixed | Fixed
9 | Voicemail |  |  | once we closed perticular voicemail , still voice mail will be playing background | apps like whatsapp have a similar approach, still if this is something we need to have, it can be implemented | The voice issue is clear now but once we open multiple voicemails the privious voicemail doesn't close. | Voice issue is still there once And one more when we open multiple voicemails the privious voicemail doesn't close.
10 | Voicemail |  |  | In the voicemail, if I click on the play button it does not play and another click button appears. It plays when I click on the second play button. | Fixed | yes its done | Fixed
11 | Refresh |  |  | once we refresh or change tabs full app is not getting refresh- which makes app edge line looks broke - or we need to remove that broke line and make second and third window line starts from the edges of phone | Clarification needed. | - | Ask Me
12 | delete button from phone tab |  |  | it is not deleting numbers once we press hold the button continously | Assigned to Sarika/Fixed/Merged/Deployed to tmp369links |  | It is deleting all the numbers at once. it will be better it should delete one by one.
13 | IM |  |  | Cursor is not coming directly once we try to send a message to perticular person | Assigned to Ankita/Fixed/Merged/Deployed to tmp369links | yes it is working but in second time.but in saumya's laptop it does'nt. | yes working
14 | IM |  |  | Messages are not in proper order - text font is bigger and we need date stamp |  | -
15 | Recent tab |  |  | there is more space on the header.. | Assigned to Sarika/Fixed/Merged/Deployed to tmp369links | Yes it's fine | Yes better but there is no scroll bar in the page
16 | Video call from phone tab and contacts |  |  | once we initated video call the dialing screen is going down and disconnect button is half visible | Fixed/ Needs feedback | Yes it's fine | yes working fine
17 | Contacts |  |  | once we enter into chat page from contacts the UI border changes for second and third window | Assigned to Ankita/Fixed/Merged/Deployed to tmp369links | Yes it's fine | yes working fine
18 | send SMS |  |  | mouse intersecion is not coming directly after clicking on Send SMS | Assigned to Ankita | It is not working on IM tab | it is not same as point number 12 this is about SMS not chat
19 | Phone Tab |  |  | Clicking on calling icon should be able to initate last call | Assigned to Arpita/Fixed/Merged/Deployed to tmp369links; for VC: Assigned to Arpita/Fixed | Yes it's fine | yes working fine for voice call only.. video call its not working
20 | Chat |  |  | Emojis are not there | Not a bug/ Will be taken up after bug fixing | -
21 | Phone tab |  |  | Star is not present in dial pad | Assigned to Arpita/Fixed/Merged/Deployed to tmp369links | Yes it's fine | yes now its there but can we separate 0 and + (0 on top and +on bottom)
22 | contacts |  |  | No match found should be displayed when searching invalid contact | No match found should be displayed when searching invalid contact | Yes it's fine | yes working fine
23 | IM |  |  | Message options are not there in the chat window like delete, retry,unsend | Not a bug/ Will be taken up after bug fixing | -
24 | IM |  |  | If that person is offline then also show online. |  | -
25 | Contacts tab |  |  | presence feature is not there in contact tab | Assigned to Sarika/ Implemented | -
26 | phone tab- third window |  |  | icons and text are not in proper order.. seems like we need to change the icon sizes | Fixed/ Needs feedback | Yes it's fine | No it is not in proper order
27 | Login page |  |  | Remember me option is not there | Assigned to Aleem/Implemented/Merged/Deployed to tmp369links | -
NEW
28 | phone-tab |  |  | -when we dial any number from the keyboard and if we want to delete that number from the backspace it doesn't work.
| NEED TO ADD |  |  | when we didn't refresh app 3-4 hours
|  |  | PHONE TAB THIRD WINDOW | 1- call is ringing but sometimes the popup is not coming.
Phone tab | which call is coming video or audio |  | HOME PAGE | 2- signal is not coming. | 2- signal is not coming.
Recents | Scroll bar |  | PHONE TAB | 3-When I press enter after entering my extension number, the page refreshes instead of going through the call.
Icons | .whenever we move our cursor into the refresh icon it should show the name of the refresh button and the logout button. |  | CONTACT | 4- I'm not able to search users by the keyboard key like Enter in the contact tab.
IM | Search bar for name searching |  | CONTACT | 5- when we call from the contact tab it's shows undefined in voice call. | Assigned to Aleem/Implemented/Merged/Deployed to tmp369links
|  |  | Phone Tab | sometimes it's happening When we are in IM tab and at that time we have a video or audio call and we pick up the call then we do not see the third window.
|  |  | CONTACT | 6- sometimes the screen is not fixed when we are on a video call.
AFTER REFRESHING THE PAGE
|  |  | IM | 7. last msgs are not coming on screen.. we need to scroll down to see the msgs and it is not coming on top of screen also .
|  |  | After login | 8. first, it will display only first window and then other windows.
|  |  | Refersh | 9. in refresh first window is not refreshed other two are refreshed only.
|  |  | video call from phone tab | 10. video is paused, when the person is using the hold and mute feature. same issue with recents.
|  |  | Mute | mute is working but the icon is not changing when we mute & unmute.
|  |  | voicemails | functionality is not working properly when we open voice mail sometimes it works fine and some time both recording play simiuntancly even after closing that recording.
|  |  | IM Tab | I have sent the last message to Anjali, so I should see it above, but it is not happening.
|  |  | Login Page | if we are giving wrong credentials that sign in button is going down
|  |  | IM Tab | IM chat messages messed up
example: if A login and chat with B after login and logout messages are there - working fine
but if C login from same system( where A logged in) and chat B - the previous messages of A is also visible in this user.
|  |  | IM Tab | check withthe below credentials
sflores@fireflytele.com
test@123
fireflytele
anotherr user IM is working fine.. but for this use,r only outgoing is working fine.
|  |  | Phone Tab | 1- Call waiting is working fine but when I disconnect the call from another person, the first person automatically goes on hold.
2- call waiting announcement or music is not coming for second person.
3- Sometimes voice call button is not working which doesn't invoke calling window.
4- call waiting- suppose A is in call with B and C call B then voice is one way - B is not able to hear C but C is able to hear B.
|  |  | IM Tab | 5- IM- last message in the chat is not showing in the IM contact list only the message which another person sent last is showing.
|  |  | Phone Tab | 6- A, B, and C are on the call waiting and B cut the call but still, B is on call.
7- Sometimes voice call button is not working which doesn't invoke the calling window.
|  |  | IM Tab | 8- online presence - after logout also it is showing online still.
|  |  | IM Tab | 9. if the person is online then also it is showing offline status(sometime)
|  |  | Third window | 10.Third window is not coming after lifting the call.
|  |  | Refresh | 11. It will refresh only the second and third windows.
|  |  | Home Page | 12.when we move next module the screen is breaking and after 3,4 seconds it will come.
13- If we didn't use application for sometime so the signal is not working for using application we have to refersh the app again .
FOR HUB369LINKS
|  |  | Phone Tab | Conference Icon is not there
|  |  | Phone Tab | When I press enter after entering my extension number, page is refreshes instead of going through the call
|  |  | video call from phone tab | screen is not fixed that time